## UAT_Cycle_1_PostEntitle
Product | Total # of Scripts Planned | Total # of Scripts Executed | Execution Status | [7 empty] | Total # of Scripts N/A
|  |  | Passed | Failed | No Run | Not Executable | In Progress | Not Completed | Blocked | Pending Validation
TON Retirement - Phase 3
WIRES/FTI | 41 | 36 | 35 | 0 | 0 | 5 | 0 | 0 | 0 | 1 | 0
|  |  | 85.37% | 0% | 0% | 12.2% | 0% | 0% | 0% | 2.439% | 0%
ACH | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
AT | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
IR/CR | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
AE | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Billing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
GE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CCAP/Forms | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
UAT_Cycle_1 | 82 | 77 | 76 | 0 | 0 | 5 | 0 | 0 | 0 | 1 | 0
Total |  |  | 92.68% | 0% | 0% | 6.098% | 0% | 0% | 0% | 1.22% | 0%

## UAT_Cycle_1_PostTrans
Product | Total # of Scripts Planned | Total # of Scripts Executed | Execution Status | [7 empty] | Total # of Scripts N/A
|  |  | Passed | Failed | No Run | Not Executable | In Progress | Not Completed | Blocked | Pending Validation
TON Retirement - Phase 3
WIRES/FTI | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ACH | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
AT | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
IR/CR | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
AE | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Billing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
GE | 3 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 33.33% | 66.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CCAP/Forms | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
UAT_Cycle_1 | 14 | 14 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | 85.71% | 14.29% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## UAT_Cycle_1_PostTrans FallBack
Product | Total # of Scripts Planned | Total # of Scripts Executed | Execution Status | [7 empty] | Total # of Scripts N/A
|  |  | Passed | Failed | No Run | Not Executable | In Progress | Not Completed | Blocked | Pending Validation
TON Retirement - Phase 3
WIRES/FTI | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ACH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
AT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
IR/CR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
AE | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Billing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
GE | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CCAP/Forms | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
UAT_Cycle_1 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## Defect Totals
Business Severity | New | Open | In Progress | Re-Open | Ready for Re-test | Fixed | Closed | Assigned to Vendor | Deferred | Totals
Critical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
High | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
Medium | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 3
Low | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Totals | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 0 | 7
Defect ID Numbers Pertaining to Each Status
| Defect IDs - New Status | Defect IDs - Open Status | Defect IDs - In Progress | Defect IDs - Re-Open Status | Defect IDs - Ready For Retest | Defect IDs - Fixed Status | Defect IDs - Closed Status | Defect IDs - Assigned to Vendor | Defect IDs - Deferred Status
|  |  | 459 |  |  |  | 444
|  |  | 460 |  |  |  | 439
|  |  | 461 |  |  |  | 435
458

## Defect Summary
Defect ID | Status | Business Severity | IT Priority | Summary | Application | Submitter | Assigned To | Project | Detected on Date | Environment Found | Cycle | Comments | Possible Resolution/Dev Comments
UAT DEFECTS
459 | Assigned / In Progress | 3-Medium |  | Kate noticed that the items listed on the Special Security page for ACH Initiation were all set to FALSE on GE. Can you please verify if this is as designed. To replicate, go to the Customer Product page > ACHINITIATION > Special. The Special Security page will appear, as displayed below: | Internet - COL: Umbrella | XXX | XXX | TON Retirement Phase 3 | 2006-09-07 | UAT | 2 | Will code/logic be changed in Phase 3 or Phase 4? Is there a manual work around for this issue if the code is not changed? I believe that logic will be changed in phase 3. Lets verify this during the call.
460 | Assigned / In Progress | 4-Low |  | On the Customer Details Page, Advance Tokens are listed for converted customers. Typically when a new customer is created, these tokens are sent out to the SA(s) to assign to new users. With Conversions, will these tokens be sent out as well (ie: Customer has users that will now need a token)? According to requirements, these tokens should be setup in advance and sent via conversion package so Pass to Pin (ie: AT only) users will have them available at time of redirect. So basically want to make sure that if these tokens are sent out in advance that they are not sent again once conversion has taken place. | Internet - COL: Umbrella | XXX | XXX | TON Retirement Phase 3 | 2006-09-07 | UAT |  | Waiting for Kip's comments before closing this defect out. | Assigning to Kip per Woody. Kip, can you confirm where the figure used for the Advanced Tokens on the Customer Detail page is captured from. I attached a screen shot of the field I'm talking about. So for instance, Customer ALLOYZ has a -2 for the Advanced Token field, which means that 2 tokens are required to be sent out to the SA of the customer. If you have any questions, please don't hesitate to ask.
461 | Assigned / In Progress | 4-Low |  | For a Pin to Pin user, Patrick logged the following issues with the UI in relation to the UI specs. 1) The words "Express" and "Challenge" in "Express Password Reset Challenge¿" are missing from the first intersticial page. Instead the beginning of the paragraph reads, 'You'll also be asked to set up your Password Reset Questions once you've...' 2) When entering either less than 6 chars or not entering at least one number for the password reset, we get the incorrect popups. The following messages appear respectively, 'Passwords must contain at least one numeric character, please re-enter your password' and 'Password must be at least 6 characters, please re-enter your password. According to the UI spec, this is what should be displayed, 'Please re-enter your password. Passwords must be at least 6 characters long and contain at least one numerical character and one alphabetic character.' | Internet - COL: Umbrella | XXX | XXX | TON Retirement Phase 3 | 2006-09-08 | UAT |  | Can these be deferred to Phase 4?
Other Defects | [5 empty] | XXX
453 | Assigned/In Progress | 3-Medium |  | When a user is currently in application and scoop is run, will the user get locked out or will the user get kicked out? How does this occurr in Phase 3 and will this change during Phase 4? |  | XXX | XXX | TON Retirement Phase 3 | 2006-08-31 | QA |  | Per discussion with Joe Vitale, this defect severity is changed from HIGH to MEDIUM. Upon retesting ACH Customer migration with defect 459, if this problem persists, it will be deferred to Phase 4.
Current Execution Timeline
1) | Still executing templates and limits

## Test Envir Outages
ID | App | Environment | Start Date / Time (CT) | Source of Problem | Incident Resolution Date/Time | Incident Duration (hrs) | Notes/Comments/Root Cause | Impact on Project
|  |  |  | Total Hours Test Env Down During Testing |  | 0